
**Maine Continuum of Care**

**Project Timeline**

On Tuesday, September 16, 2004 HUD released the Notice of Funding Availability (NOFA) for the Continuum of Care Program Competition.

**NOFA TIMELINE**

**FOR THE PROJECT COMMITTEE**

**DRAFT**

**9-19-14**

**Fri. Sept. 19, 2014 Project Committee Meeting 9a-12n**

**At MaineHousing**

**Fri. Sept. 19, 2014 Post Due Dates for Project Applications**

**Fri. Sept. 26, 2014 Response from Applicants who intend to**

**Apply.**

**Mon. Sept. 29, 2014 Steering Committee 10:00 am-12:00 pm**

**Fri. Oct. 3, 2014 Email check in to see who is coming in**

**(Heather L. to inform committee of who is**

**Applying for renewal or reallocation &**

**Bonus & New Project)**

**Fri. Oct 3, 2014 New Renewal Projects to submit**

**monitoring information to chairs**

**Mon. Oct. 6, 2014 Steering Committee 10:00 am-12:00 pm**

**Fri. Oct. 10, 2014 Project Committee Meeting to monitor**

**First time renewal projects and chairs to**

**Assign projects to members for compliance review.**

**Fri. Oct 10, 2014** **E-SNAPS NEW PROJECTS and FIRST**

**TIME RENEWALS APPLICATIONS**

(former Exhibit 2) **DEADLINE TO**

**COMPLETE by 5:00 pm.**

**Mon. Oct 13, 2014 Holiday**

**Wed. Oct. 15, 2014** **E-SNAPS RENEWAL PROJECT**

**APPLICATION** (former Exhibit 2)

**DEADLINE TO COMPLETE & submit in**

**e-snaps by 3:00 pm.**

**Thu. Oct. 16, 2014 8:00 am-1:00 pm Review & rank**

**All new projects & first time renewal**

**Applications**

**Fri. Oct.17, 2014 Notify Projects whether their application**

**will be included in the e-snaps submission**

**Mon. Oct. 20, 2014 Steering Committee 10:00 am-12:00 pm**

**Thu. Oct.23, 2014 Program Compliance Review by Project**

**Committee (location TBD) 9:00am-3:00 pm**

**(Hosted by OHI in Bangor)**

**Mon. Oct. 27, 2014 Steering Committee 10:00 am-12:00 pm**

**Tue. Oct. 28, 2014 MaineHousing submits NOFA application**

**in e-snaps**

**Thu. Oct. 30, 2014 HUD FINAL due date for NOFA Application**